## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-07-7-g-fundsinhighplaces
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a User I want to make an account so that I can join the site and access the needs. | Given valid user information when a user tries to create an account then I expect the account to be added to the database. | Pass | MZ; 10-23-2023
| Given invalid user information when a user tries to create an account then I expect an error to be returned. | Pass | MZ; 10-23-2023
As a helper I want to login and logout so that I can view and support the non-profit. | Given a valid ID is received when a helper logs in then I expect the helper features to be visible and actionable | Pass | MZ; 10-27-2023
As a manager I want to login and logout so that I can access and modify the food needs in my cupboard. | Given a valid ID is received when a manager logs in then I expect the manager features to be visible and actionable | Pass | MZ; 10-27-2023
As a manager, I want to be able to add/remove food needs so that I can take down needs when they are fulfilled and add when new materials are needed. | Given the inputs are all valid when I add a need then the need will be added to the cupboard and displayed | Pass | CAV II; 10-29-2023
As a Manager, I want to be able to edit my food needs depending on what I will need at the time. | Given valid need information when a manager tries to create a new need, then I expect the need to be added to the cupboard. | Pass | CAV II; 10-29-2023
| Given invalid need information when a manager tries to edit a need then I expect an error to be returned. | Pass | CAV II; 10-29-2023
As a helper, I want to be able to browse for needs so that I can know what materials need to be donated. | GIVEN I submit a request to search for all needs containing a string WHEN needs exist in the cupboard THEN the system should display a list of needs containing the search of 200 (OK) | Pass | SDP; 10-28-2023
| GIVEN I submit a request to search for all needs containing a string WHEN needs do not exist in the cupboard THEN the system should display an empty list of needs containing the search of 200 (OK) | Pass | SDP; 10-28-2023
As a Helper, I want to create a funding basket so that I can fund my own needs. | Given the correct input parameters when I call the constructor then I expect them to generate it. | Pass | KN; 10-27-2023
| Given an incorrect parameters when I call the constructor then I expect an error to occur. | Pass | KN; 10-27-2023
As a Helper, I want to add and remove food needs from the funding basket so that I can store my purchases. | Given I call addSupportedNeed() when a need exists in cupboard then the need should be added to the fundingbasket and a status code of 200 (OK) | Pass | KN; 10-28-2023
| Given I call removeSupportedNeed() when a need exists in the fundingbasket then the need should be removed from the fundingbasket and a status code of 200 (OK) | Pass | KN; 10-28-2023; Deleting Needs deletes the enitre need instead of 1. Fixed
| Given I call addSupportedNeed() when a need DOES NOT exist in cupboard then return null and a status code of 200 (OK) | Pass | KN; 10-28-2023
| Given I call removeSupportedNeed() when a need DOES NOT exist in the fundingbasket then then return null and a status code of 200 (OK) | Pass | KN; 10-28-2023
As a Helper, I want to Check-Out my funding basket so that I can purchase the food needs I want. | GIVEN I submit a request to check out needs WHEN needs are in the fundraising basket THEN the system should update the number of needs required and a status code of 200 (OK) | Pass | SDP; 10-28-2023; Need quantity in cupboard does not delete when 0. Fixed
| GIVEN I submit a request to check out needs WHEN needs are in the fundraising basket THEN the system should remove all needs in the fundingbasket and a status code of 200 (OK) | Pass | SDP; 10-28-2023
As an manager, I want my needs cupboard to save with changes so that Helpers can see the most current list of needs and have outdated needs accurately removed. | GIVEN the cupboard exists WHEN a manager adds, removes, and modifies a need in the cupboard, THEN I expect the JSON file to save the changes |  |  | Pass | KN 11/14; it works well. No issues.
As a helper, I want the contents of my funding basket to be saved so that I can still view and edit it when I come back later. | GIVEN a helper adds/removes needs from Funding Basket WHEN the needs exists on the cupboard or fundingbasket THEN the changes should be saved on a file. |  |  | Pass | SP 11/14; when I go back to the helper page, it stays there.
| GIVEN a helper adds/removes needs from Funding Basket WHEN the needs exists on the cupboard or fundingbasket THEN the changes should display on the web application. |  |  | Pass | CVG 11/14; Works fine.
As a user, I want my account to be saved so that I can log in later. | Given the account username when I create an account then I expect the account to be saved. |  |  | Pass | MZ 11/14; yep, logging back in with the same username works and saves.
As a helper I want to write personalized messages with my donation so that others can see why i donated. | GIVEN A message is not empty WHEN a helper checks out THEN I expect the message to be saved and displayed on the landing page. |  |  | Pass | MZ 11/14; I can, it works!
| GIVEN A message is empty WHEN a helper checks out THEN I expect the message not to be saved and not be displayed |  |  | Pass | MZ 11/14; empty message doesn't save. It's good.
As a manager, I want to get notified when a need is fulfilled so that I can modify my needs cupboard to reflect the completed goal and set new ones | GIVEN a helper checks out their funding basket WHEN the helper presses the checkout button THEN a string should be added to a list of all checkouts that a manager can access. |  |  | Pass | SP 11/14; All checkout messages successfully send to the manager.
| GIVEN a manager wants to see all past checkouts WHEN the manager presses a see all past checkouts button THEN a manager should see the list of all past checkouts |  |  | Pass | KN 11/14; perfect
| GIVEN a helper checks out their funding basket WHEN the helper presses the checkout button THEN a string should be added to a list of all checkouts which is saved on a file |  |  | Pass | SP 11/14; it's true. Works fine.